## Slide 1: Change Activities
Waterfall Project Plan

## Slide 2
Key Activities by Phase
Design
Develop and Test
Implementation
Operations
Design Workshops
Develop Change Management Plan
Change Impact Analysis
Engagement Plan
Communication Plan
Learning & Development Plan
Align and Engage Leadership and Stakeholders
Train and Coach Internal Change Network
End User Training
Execute and Update Change Plan
Support End User Training
Post training evaluation
Align and Engage Leadership and Stakeholders
Go Live Support
Execute and Update Change Plan
Sustain the Change
Identify Lessons Learned
Business Needs Analysis
Scope & Requirements
Plan Change Readiness Assessment
Identify Change Sponsor
Identify Change Manager
Stakeholder Analysis
Schedule interviews and workshops
Conduct Initial Change Readiness Assessment (CRA)
Conduct confidential interviews
Develop and present Change Strategy
Approval of Change Strategy by Project and Change Sponsor
Key Project Activities
User Acceptance Testing
User
Documentation
Execute and Update Change Plan
Measure and Monitor Change Adoption
Manage Risk
Develop, Deliver and Monitor On-Going Communications
Participate in UAT
Update components of the Change Plan
Initiation and Analysis
Phase
Key Change Activities