## Change Plan
Change Implementation Plan
Project Phase | Category | Change task | Objective/Task | Comments | Start Date | By when | Involved | Tools | Subject | Questions | Complete (Y/N)
| Leadership Interviews | Leadership Alignment Strategy | Devise a strategy to align leaders with the change
| Leadership Interviews | Leadership Engagement | Conduct interviews with leadership using an alignment questionnaire
| Leadership Interviews | Stakeholder Analysis & Engagement | Determine which leaders to engage
| Leadership Interviews | Leadership Engagement | Schedule leadership interviews
| Leadership Interviews | Leadership Engagement | Execute leadership interviews using an alignment questionnaire
| Leadership Strategy | Leadership Strategy Formulation | Identify common themes from interviews and prepare a presentation
| Leadership Strategy | Stakeholder Analysis & Engagement | Analyze leadership interviews
| Leadership Strategy | Stakeholder Analysis & Engagement | Compile interview summary into a presentation
| Stakeholder Assessment | Stakeholder Assessment | Identify stakeholder groups and their desired commitment levels
| Stakeholder Assessment | Stakeholder Analysis | Determine optimal methods for conducting stakeholder analysis
| Stakeholder Assessment | Stakeholder Analysis | Conduct stakeholder analysis
| Stakeholder Assessment | Stakeholder Analysis & Engagement | Share stakeholder analysis summary with relevant parties
| Change Network | Change Network Planning | Use stakeholder analysis to identify Change Network for new project
| Change Network | Change Network Confirmation | Verify Change Network Candidates
| Change Network | Communication & Change Network | Ensure Change Network candidates are ready and able to participate
| Change Network | Engagement & Change Network | Organize initial Change Network meeting
| Change Network | Engagement & Change Network | Schedule regular bi-monthly/monthly meetings
| Change Impact | Change Impact Assessment | Define scope of Change Impact Assessment
| Change Impact | Change Impact Assessment | Evaluate Change Impact using a tracking tool
| Change Impact | Change Impact Assessment | Develop Change Impact Assessment summary
| Change Readiness Assessment | Define Change Readiness Assessment | Define scope of readiness assessments
| Change Readiness Assessment | Develop Change Readiness Assessment | Develop readiness assessment surveys and key metrics
| Change Readiness Assessment | Develop Change Readiness Assessment | Distribute surveys at designated times
| Change Readiness Assessment | Compile change Readiness Assessment | Compile findings into a report and share with leadership
| Change Readiness Assessment | Archive Change Readiness Assessment | Archive Readiness Assessments in a centralized location
| Case for Change | Case for Change | Create initial change messaging
| Case for Change | Case for Change | Develop case for change messaging
| Case for Change | Case for Change | Approve case for change messaging points
| Change Management Strategy | Develop Change Management Strategy | Incorporate stakeholder assessment, change impact assessment, readiness assessment, case for change, and change network into strategy
| Change Management Strategy | Present Change Management Strategy | Present Change Strategy to leadership, project team, and stakeholders
| Communication | Communication Plan | Create an initial communication plan
| Communication | Communication Approval | Develop a communication approval matrix
| Communication | Communication Roadmap | Design an initial communication roadmap
| Communication | Communications | Draft initial communications
| Communication | Communication Plan | Refer to detailed Communication plan
| Training | Training Plan | Refer to detailed training plan