## Definitions
Change Type Desciption
Organizational Change: When a company changes its structure, it's undergoing organizational change. This might include new roles, different team setups, reporting adjustments, or even relocating. It can also include joining or acquiring other companies, or making big internal changes.
Process Change: This refers to changes in how a company gets things done. The goal of process changes is usually to work smarter or produce better results. These changes can affect everything from the overall operation to individual tasks.
System/Technological Change: This change has to do with updating or introducing technology in a company. This can include anything from software updates, hardware upgrades, to introducing entirely new systems, like a customer management system, or moving to cloud-based services.
Cultural Change: This is when a company works to change its core beliefs, values, and accepted behaviors. It's often challenging because it means changing deeply held attitudes and ways of doing things.
Strategic Change: This is when a company decides to change its overall game plan. It's often driven by outside forces, like changes in the market, competition, or rules and regulations. This could include a new mission, a different vision, or revised strategic goals.
Impact of Change ( People, Process, Technology) H, M, L
People:
Low Impact (L): Small changes that affect a few people, like slight role adjustments.
Medium Impact (M): Changes that affect a team or department, such as team restructuring.
High Impact (H): Big changes affecting most or all of the company, like major policy or structural changes.
Process:
Low Impact (L): Small tweaks to how things are done, that don't disrupt the overall flow of work.
Medium Impact (M): Changes to a larger process or several processes, needing some retraining or adjustments.
High Impact (H): Major changes to how the whole organization works, requiring significant adjustment and training.
Technology:
Low Impact (L): Small updates to existing technology, easy to adapt to with little or no training.
Medium Impact (M): Replacing existing technology with something new that needs learning, or deploying new hardware in a department.
High Impact (H): A big tech overhaul that affects the entire company, requiring extensive training and causing significant disruption.
Stakeholder Impact H, M, L
Low Impact (L): The changes won't drastically affect the stakeholder group's day-to-day operations, roles, or responsibilities. Minimal disruption or adjustment is expected, and they may require little to no training to adapt to the changes.
Medium Impact (M): The changes will affect the stakeholder group to a moderate degree. Their roles, responsibilities, or routines may change somewhat, requiring some adjustment and potentially some retraining. There could be a fair amount of disruption, but the group is not entirely transformed.
High Impact (H): The changes will significantly affect the stakeholder group. Their roles, responsibilities, or routines may change dramatically, requiring extensive retraining and adjustment. The changes could potentially transform the nature of the group, causing substantial disruption and necessitating significant support to adapt.

## Change Impact
Change Impact Assessment
Change Type | Affected Business Areas | Locations (or Sites, Operational Area) | High Level Change Description | Stakeholder Impact | Impact of Change H, M, L | Column1 | Column2 | Key Assumptions | Mitigation Strategy | Additional Notes
Organizational Change, Process Change, System/Technological Change, Cultural Change, Strategic Change |  |  | High-level description of the upcoming change | H,M,L | People | Process | Technology | Considerations of role types, seniority levels, implementation timelines, IT needs, and reporting hierarchies | Communication, training tactics or tools to assist with the adoption of the change
Organizational Change | Distribution, Delivery, Customer Services | Vancouver, B.C | Moving distribution warehouse from Ontario to B.C | H | High | Medium | High | The existing warehouse staff have the necessary skills and are willing to relocate. The market in B.C is ready to accommodate a new distribution warehouse. | Implement a comprehensive change management strategy involving clear and consistent communication, employee engagement activities, and thorough training for relocated or newly hired employees in B.C. | Early communication about this change to all affected stakeholders will be essential to ease the transition.
Process Change | Design, Production | New York | Implementing a new design software to streamline design processes | M |  |  |  | Designers and production teams have the basic IT skills required to adapt to new design software. | Offer comprehensive training for the new software, and establish a help desk for addressing issues during the transition period. | Engage with software provider for ongoing support post-implementation.
System/Technological Change | Marketing, Sales | Global | Upgrading to a new Customer Relationship Management (CRM) system | H |  |  |  | Existing team members are adaptable and open to learning new technologies. The new CRM system will improve efficiency and customer experience. | Organize comprehensive training sessions, develop user manuals, provide a grace period for adoption, and appoint superusers to assist others. | Continuous monitoring and support will be necessary post-implementation to ensure smooth transition.
Cultural Change | Entire Company | Global | Implementing a new sustainability initiative across all business areas | L |  |  |  | Employees are open to embracing new sustainability practices. Consumers appreciate brands with strong sustainability credentials. | Communicate the reasons behind the change clearly, offer training on new sustainability practices, celebrate early adopters. | Continuous reinforcement and recognition are key to instilling the new cultural norms.
Strategic Change | Entire Company | Global | Shifting from a fast fashion model to a focus on durable, high-quality clothing | H |  |  |  | Customers will accept the change in product and pricing. The manufacturing process can be adapted to meet the new quality standards. | Conduct market research and customer surveys to understand consumer preferences, communicate the change widely, and ensure high-quality production. | Engaging stakeholders in early stages of planning will assist in successful execution.